## Sheet1
Number | Real hours | Task | Business requirement | Order | Estimation | Notes
DEI-1-1 | 2 h 30 min | Set up project | Set up your Git repository |  | 2 hour | 1
DEI-1-2 |  | Create README | Create a README.md |  | 1 hour
DEI-2-1 |  | Total maintanence cost | What’s the total maintenance cost |  | 1 hour
DEI-2-2 |  | Minutes of downtime | How many minutes of downtime have there been |  | 1 hour
DEI-2-3 |  | Maintenance events count | How many maintenance events occurred |  | 1 hour
DEI-2-4 |  | Breakdowns count | How many breakdowns (unplanned) happened |  | 1 hour
DEI-2-5 |  | Average downtime | What’s the average downtime per event |  | 1 hour
DEI-3-1 |  | Read tables or CSV | Design a robust pipeline |  | 2 hour
DEI-3-2 |  | Clean and transform | Clean and transform: |  | 2 hour
DEI-3-3 |  | Fact table | Produce a fact_table |  | 2 hour
DEI-3-4 |  | Fact table export | Export your results |  | 1 hour
DEI-3-5 |  | Document pipeline | Document your pipeline steps |  | 1 hour
DEI-4-1 |  | Unit tests | Write at least two unit tests |  | 2 hour
DEI-4-2 |  | Edge cases | What edge cases did you consider |  | 1 hour
19 hours
|  |  |  | Deadline: | 2026-01-20